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Sprouts House Outdoor Learning – Requested Report
Project Manager Name
Moses Thompson and Brit Palomarez
Requested Metrics
Please provide all applicable metrics for your Strategic Investment.
With generous support from the UA Campus Sustainability Fund, School Garden Workshop accomplished all of our intended metrics for the Sprouts House Outdoor Learning Laboratory.  Metrics include:
· Direct Service Impacts:
· UA students served through hands-on workshops: 168
· TUSD students served through hands-on workshops: 108
· K-12 educators served through hands-on workshops: 163
· Tucson community members served through special events: 655
· Indirect Service impacts: 
· 9,780 K-12 students impacted by 163 educators served
· Total Gallons of Rainwater Storage Installed:  6,525
________________________________________________________________________
· Total UA Students, Direct Service:
· Trowbridge + Smith = 50 students
· Manzo field trip= 24
· Pueblo field trip= 34
· Total TUSD Students
· Total K-12 Educators:
· Conference fieldtrip: 45
· GA teachers: 30
· ELC teachers: 18
· Stemazing teachers 20
· Mansfeld Staff Professional Development: 50 

· Total Community members:
· Dedication ceremony: 200
· Dinner event: 50
· Art show: 150
· STEM night:
· Mansfeld PTA: 15
· EEF Mixer: 25
· Ward 6 Mixer 25
· Church Group: 25 
· UA President’s Club: 100
· UA President’s visit: 40
· Neighborhood event sponsored by Miranda Schubert: 25
Project Accomplishments
Please describe what was accomplished through this project. Be as descriptive and specific as possible. Your response could include: 
The Sprouts House Outdoor Learning Laboratory project successfully accomplished all benchmarks listed in our proposal while meeting Arizona State Historic Preservation requirements and enriching public education, student engagement, and community awareness. With generous support from the UA Campus Sustainability Fund, we procured and transported a 20 foot shipping container for long-term tool and equipment storage, excavated and filled 8 in-ground garden beds, laid 300+ feet of drip irrigation, installed 3 ADA accessible pathways on site, and secured functional outdoor classroom equipment that will outlast the wear and tear of the summer sun, high traffic programs, and eager K-12 learners. This support helps to improve the long-term use of Sprouts House as a teaching and learning environment. 
In addition to the sustainability capital improvements, the Sprouts House Outdoor Learning Laboratory (SHOLL) project provided opportunities for hands-on workshops for UA students, K-12 students, and K-12 educators. During this grant’s funding cycle we provided hands-on sustainability workshops for 168 UA students, 108 Tucson Unified School District K-12 students, and 163 K-12 educators from across the region and beyond. Participants gained skills and resources for adopting sustainability practices in both K-12 school settings and at home. And this is just the beginning. The Sprouts House Outdoor Learning Laboratory made possible with the help of the Campus Sustainability Fund, sets in motion sustainability programming that will produce similar metrics each school year going forward. 
It might also be mentioned that the SHOLL also serves as a model of sustainability for the community that surrounds Sprouts House (SH) and a highly visible example of the UA’s commitment to sustainability practices. Neighbors, teachers, UA and TUSD students, passersby and visitors behold the SHOLL as intentional and successful infrastructure meant to demonstrate that sustainable practices work. SHOLL also underscores a key way the UA can inspire others to adopt those practices and young people to appreciate them as “normal” and smart elements of a sustainable desert landscape. 


Recommendations 
What recommendations do you have from your time leading this project? Your response could include: 

The SHOLL is a permanent installation of the School Garden Workshop’s Sprouts House. Its sustainability profile built within a once disinvested corner of the neighborhood stands out as forward looking, efficient, and effective.

Essential equipment such as a shipping container, drip irrigation, pavers, tables and chairs were purchased to outfit the learning space and support its long-term success. UA students from the School Garden Workshop course as well as others from around campus were key participants in the establishment of the SHOLL environment and will continue to help with maintenance support and activation of the space going forward.

Maintenance of SHOLL’s multiple elements is central to the official job description of the Sprouts House Program Manager. Security of the SHOLL as well as SH overall is the responsibility of UA Campus Police and UA network security protocols. 

Next academic year’s activities that reflect our support from the Campus Sustainability Fund include: 
· Fall and Spring Semester UA student sustainability workshops will be held at Sprouts House
· Fall and Spring Semester Pre-K-12 educator sustainability workshops will be held at Sprouts House
· Fall and Spring Semester K-12 student field trips to Sprouts House


What recommendations do you have for future grant recipients and project leaders?
We don’t have any recommendations at this time. Thank you!
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